## FunctionTest
No. | Test name | date | Test description (date) | Input value | Expected output | Issues / noIssue | solving with (date) | accept solution?(yes/no)(date)
1 | Create New Organism | 2022-11-03 | Create new organism via creating form window on Organism List view site. (03/11/22) | Test, TestSpeice, | New Organism record with class short name + sequence number Audit Model field automatically and correctly recorded. All Input fields correctly recorded. | pass
|  | 2023-03-30 | Create new organism via creating form window on Organism card view site. (30/03/23) | login user:uqwzhon4, writer; create:Aa test | New Organism record with class short name + sequence number Audit Model field automatically and correctly recorded. All Input fields correctly recorded. | pass
2 | Update New Organism | 2022-11-03 | Update an existed Organism record via updating form on Organism Detail view site. (03/11/22) | Change Organism Name, Change fields value. | In case of with same Organism Class can be updated by name, In case of updating with the Organism name in different class, cannot be updated, return warning message. Changed fields will be recorded and updated on the site. Input error will show message e.g., case 2. Updated time and user will be recorded | pass
|  | (30/03/23) | Update an existed Organism record via updating form on Organism Detail view site.(30/03/23) | add Strain type, change organism name in same class, change organism name in different class. | as above | pass
3 | Delete Organism |  | Delete Organism on List View site (03/11/22) No delete on List View | Click delete button | Deleted Organism will not display on the site astatus changes to -9, record still in DB | pass
|  | (30/03/23) | Delete Organism on Detail View site (30/03/23) | Click delete button | user not Admin, button cannot click | pass
4 | Search and filtering test | (04/11/22) | Test ListView/CardView site search and filter functions. (04/11/22) | Organism Name | Returning correctly with organism name contains input string on each page | List  card view switch broke filtering. | solving with jQuery code block to switch two templates (07/11/22)
test filter bar with global search
5 | Ldap User not in User list |  | Ldap user not in app user list cannot login and access any site (04/11/22) | Ldap user and password | Cannot login any site | pass
6 | AppUser Permissions: Only read |  | AppUser without ‘staff’ permission, Cannot do updating, creating, importing data (04/11/22) | AppUser log in without staff permission | user can read data user cannot edit data | No redirect URL when user cannot edit data | displaying operation”create/update/delet” button when user is superuser with {%if request.user.is_superuser%}in template(07/11/22); second change, redirect to login site
7 | AppUser Permissions: Not superuser/admin |  | Appuser without ’admin’ permission, cannot delete or import data (04/11/22) | Super User update AppUser permissions=’staff’. Appuser log in | user can edit data except delete and import | pass
8 | AppUser Permissions: With superuser/admin |  | AppUser with ‘admin’ permission Can edit data and import data (04/11/22) | Super User update AppUser permissions=’admin’. Appuser log in | user can read, edit data, delete and import | pass
9 | Import Dictionary |  | go to sit http://127.0.0.1:8000/app/dict/, click import dictionary (07/11/20) | .csv dictionary | import .csv values to table dictionaries | Cannot save ‘User’; pass | add ‘acreated_by column during object creating in import functions’. Modify def save(...)in Audit Model , if there is no kwargs key word variable, then pass the following if block directly to save. Print message (07/11/22); Second change, discarding previous modification in save(...) function , just change if self.stating to not self.areacte_by.(08/11/22)
10 | test error message on modal form |  | In Taxonomy create sit, to input an existed Taxonomy name in the Organism_Name field and expected Modal form to stay on the current window with error message (07/11/20) | Organism_Name=testSpeice, which is already existed | Create Modal Form stay in the showing status with error message displaying. | Modal window pop off, after submitting the form. The error message showed but need to re-open the modal window to see the message. | currently, displaying error message on the upper level site.(07/11/22)
11 | test delete dictionary in modal window |  | choose a dictionary item, click delete button, pop up "confirm" window, click confirm. Item will be moved from displaying list and return back to the previouse window.(08/11/20) | delete | item astatus change to -9, return back. | pass
12 | test update appuser permission |  | update appuser from admin to staff, appuser only has permission to edit data but no permission to delete(08/11/20) | user.permissions=staff | cannot delete record | pass
13 | test adding multiple filters |  | add field " fields=['Organism_ID', 'Strain_Code', 'Strain_ID', 'Strain_Desc', 'Strain_Notes', 'Strain_Type', 'MTA_Document', ]" and Foreign key field Organism_name, Class to test search result(08/11/20) | all the new added filter field | correct result show in card, list view with correct pages | pass, Strain_type field filtering failed when chose and clicked filter. With dataError, DETAIL: Array value must start with "{" or dimension information. ) was the direct cause of the following exception: | implement customized filter to utils.py/Searchbar_03()(08/11/22)
14 | test import organism csv |  | refer test 9, replace dictionary to organism(08/11/20) |  |  | utf-8' codec can't decode byte 0xad in position 22: invalid start byte
15 | test UI editable table |  | dbclick table cell showing input or select with buttons HTML elements. Fields can be edited and updated. (10/11/20) | For charfield,typing test value. For select / multiselect fields, select options | data updated without error in DB and UI pages | pass, Editing two or more table cells, click one save button, will close other table cells editing conditions. | issue caused by a malcodeline window.location.reload(). (11/11/22)
16 | test Session expire time |  | after 2 mins inactive with opened application, login session should be expired | inactiv with app | logout automatically
17 | Filter side-bar display | 2023-02-14 | On page "/organism_card", choose filter items: Input or Select Options (class, name, type etc.,..). Click 'Apply' Button. Click 'reset' Button.(14/02/23) | Filter Items | 1. filter bar showing selected filter items on the top 2. the selected items display selected. 3. main div right showing result after click button | 1.the selected item 'Type' displaying uncompletedly. 2.sidebar and main div width changes as a side effect of drag-expand sidebar(UI issue) | fix sidebar width?
18 | Create New Organism | 2023-02-14 | On page "/organism_card" and "/organism_list", click "+"button, fill form inputs, click Add button. | dj modal form input and submit | create New entry in DB | pass, website not come back to previous page after submit | views.py change redirect "org_list" to redirect(req.META['HTTP_REFERER'])
19 | Create New Batch | 2023-02-14 | On page "/organism/FG_0001" , click "New Batch+"button, fill form inputs, click Add button | dj modal form input and submit | create New entry in DB | pass
|  | 2023-03-30 | On page "/organism/FG_0090" , click "New Batch+"button, fill form inputs, click Add button
20 | Create New Stock | 2023-02-14 | On page "/organism/FG_0001" , click "+"button next to Stock, fill form inputs, click Add button | dj modal form input and submit | create New entry in DB | pass
21 | create new drug | 2023-02-15 | On page "/drug_card", click "+"button, fill form inputs, click Add button. | dj modal form input and submit | create New entry "test" in DB | pass
22 | Update Organism Name in same class for Organism tables | 2023-02-16 | On page "/organism/FG_0001" , click on table cells Organism Name, type any letteres e.g.: "can…", from the drop down menu choose another Organism in same class fill form inputs, click "update changes" button | dj editable table form input and submit | Update "candida albicans" to Canacomyrica monticola , then change back | pass Key enter will submit the form | add jQuery key event prevent for key enter event
23 | Update Organism Name in different class for Organism tables | 2023-02-16 | On page "/organism/FG_0001" , click on table cells Organism Name, type any letter e.g.: "to..." choose another Organism in different class fill form inputs, click "update changes" button | dj editable table form input and submit | showing Error msg: Update failed due to ['Not the same Class'] error | pass
24 | update other fields of Organism | 2023-02-16 | On page "/organism/FG_0001" , click on table cells except Organism Name, change input, click "update changes" button | dj editable table form input and submit | update entry based on new input | 1. fields "sequence, XXX Pref…": no response 2. No panel option
25 | update Batch | 2023-02-16 | On page "/organism/FG_0001", dbclick edit icon on Section Organism Batch at row "OrgBatchID= FG_0001_01", change input cell "Batch Notes, QC_status, Supplier, Supplier Code, Stock Date, Biologist". Then click update button | dj form input and submit via htmx | update entry based on new input | pass OrgBatch ID should not show editable | add formfield attribute readonly (16/02/23)
26 | update stock | 2023-02-16 | On page "/organism/FG_0001", dbclick arrow down icon on Section Organism Batch at row "OrgBatchID= FG_0001_01" to open Section Stok, click edit icon at row "stock" change modal form input. Then click update button | dj modal form input and submit modal form | update entry based on new input | pass

## UITest
No. | Test name | Test description (date) | Input value | Expected displaying | Issues / noIssue | solving with (date) | accept solution?(yes/no)(date)
1 | Filter side-bar display | On page "/organism_card", choose filter items: Input or Select Options (class, name, type etc.,..). Click 'Apply' Button. Click 'reset' Button. | Filter Items | 1. filter bar showing selected filter items on the top 2. the selected items display selected. 3. main div right showing result after click button | a.sidebar and main div width changes as a side effect of drag-expand sidebar | fix sidebar width?